## Instructions
TEXNICA TPCS 1.0 — FABRIC CONTROL WORKBOOK
Purpose | Operational workbook for FGPO, fabric requirement, purchasing, mill production, shipment, Texnica receiving, testing, approval, inventory and cutting issuance.
1. Start | Create the customer order in FGPO Master. If no official number exists, select FGPO Pending and use a unique Temporary Order ID.
2. Requirement | Enter style consumption in Fabric Requirement. Gross and net purchase quantities calculate automatically.
3. Purchase | Create Fabric PO records and allocate ordered quantities to FGPOs.
4. Mill | Update production by Fabric PO, FGPO and Lot. Record the mill test separately.
5. Logistics | Record fabric shipment and In Transit quantities by Lot.
6. Receiving | Receive at Texnica by shipment and then by individual Roll.
7. Quality | Complete Four-Point, Internal Test and Shade Match records.
8. Approval | Fabric Approval calculates whether all gates are passed before Release for Cutting.
9. Inventory | Fabric Inventory consolidates approved, hold, reserved, issued, returned and available quantities.
10. Cutting | Issue only approved and available fabric to cutting.
Shipment Variance | Total Shipped Quantity − Order Quantity. Negative = pending; positive = over-shipment.
Receiving Variance | Actual Received Quantity − Shipped Quantity. Negative = shortage; positive = over quantity.
Color Logic | Green = completed/approved; Yellow = pending/hold; Red = failed/shortage; Gray = not started.
Inputs | Yellow cells are editable. Gray cells contain formulas and should not be overwritten.
Ownership | Each record includes Data Owner and Last Updated for traceability.
Capacity | Each operational sheet provides 300 working rows.

## Dashboard
TEXNICA PRODUCTION CONTROL SYSTEM — MASTER DASHBOARD
Customer PO visibility from material development through shipment. Click sheet tabs for full operational detail.
Open FGPO |  |  | Order Quantity |  |  | Cut Quantity |  |  | Sewing Output |  |  | Packed Quantity |  |  | In Transit |  |  | Customer Received
0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
FGPO | Style | Color | Order Qty | Fabric Status | Trims Status | PP Sample | PRR | Cutting Release | Cut Qty | TOP Sample | Sewing Qty | Inline QC | Final QC | Packed Qty | Ready to Ship | In Transit | Received Qty | Shipment Variance | Ship Date | Risk | Last Updated

## Fabric Dashboard
TEXNICA TPCS 1.0 — FGPO & FABRIC CONTROL DASHBOARD
Automatic summary by FGPO. Enter order and operational data in the detailed modules; do not type over dashboard formulas.
Total FGPO |  |  |  | Total Order Qty |  |  |  | Fabric In Transit |  |  |  | Fabric Received |  |  |  | Fabric Approved |  |  |  | Open Shortage
0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Customer | FGPO | Status | Style | Color | Order Qty | Shipment Variance | Fabric Required | Fabric Ordered | Mill Produced | Mill Test | Fabric Exported | Fabric In Transit | Texnica Received | Receiving Variance | Four-Point | Internal Test | Shade Match | Fabric Approved | Reserved | Issued to Cutting | Available | Shortage

## FGPO Master
TEXNICA TPCS 1.0 — FGPO MASTER
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Record ID | FGPO | Temporary Order ID | FGPO Status | Customer | Style | Color | Order Quantity | Ship Date | In Transit Qty | Received Qty | Total Shipped Qty | Shipment Variance | Pending to Ship | Over-shipment Qty | Produced Qty | Production Variance | Pending Production | Overproduction Qty | Data Owner | Last Updated | Remarks

## Fabric Requirement
TEXNICA TPCS 1.0 — FABRIC REQUIREMENT
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Requirement ID | FGPO | Style | Color | Fabric Component | Fabric Description | Composition | GSM | Required Width | UOM | Order Quantity | Approved Yield | Gross Requirement | Allowance % | Allowance Qty | Available Inventory | Net Purchase Requirement | Required Date | Status | Data Owner | Last Updated | Remarks

## Fabric PO
TEXNICA TPCS 1.0 — FABRIC PO
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Fabric PO Number | FGPO | Supplier | Fabric Mill | Fabric Component | Style | Color | Ordered Quantity | UOM | Unit Price | PO Amount | Order Date | Required Completion | Planned Export | Planned Arrival | PO Status | Purchase Owner | Approved By | Last Updated | Remarks

## Mill Production
TEXNICA TPCS 1.0 — MILL PRODUCTION
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Production ID | Fabric PO Number | FGPO | Supplier | Fabric Component | Style | Color | Planned Quantity | Produced Quantity | Completion % | Lot Number | Roll Quantity | Yardage / Qty | Weight | Start Date | Finish Date | Planned Export | Actual Export | Status | Data Owner | Last Updated | Remarks

## Mill Test
TEXNICA TPCS 1.0 — MILL TEST
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Mill Test ID | Fabric PO Number | FGPO | Supplier | Lot Number | Color | Roll Qty | Actual Width | Actual GSM | Length Shrinkage % | Width Shrinkage % | Torque % | Bowing % | Skewing % | Colorfastness | Wash Appearance | Hand Feel | Test Date | Tested By | Test Result | Approved for Export | Report Link | Last Updated | Comments

## Fabric Shipment
TEXNICA TPCS 1.0 — FABRIC SHIPMENT
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Shipment Number | Fabric PO Number | FGPO | Supplier | Lot Number | Roll Qty | Shipped Quantity | UOM | Shipped Weight | Packing List | Invoice Number | Container / AWB | Shipping Method | ETD | ETA | Shipment Status | Delivered to Texnica Date | In Transit Quantity | Remaining to Deliver | Data Owner | Last Updated | Remarks

## Fabric Receiving
TEXNICA TPCS 1.0 — FABRIC RECEIVING
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Receiving Number | Receiving Date | Shipment Number | Fabric PO Number | FGPO | Supplier | Packing List Qty | Actual Received Qty | Receiving Variance | Receiving Shortage | Receiving Over Qty | Expected Rolls | Received Rolls | Missing Rolls | Receiving Status | Warehouse Location | Received By | Data Owner | Last Updated | Remarks

## Roll Receiving
TEXNICA TPCS 1.0 — ROLL RECEIVING
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Roll Record ID | Receiving Number | Fabric PO Number | FGPO | Supplier | Lot Number | Roll Number | Supplier Roll Number | Color | Gross Weight | Net Weight | Actual Yardage | Actual Width | Actual GSM | Shade Group | Damaged Qty | Condition | Warehouse Location | Received Date | Data Owner | Last Updated | Comments

## Four-Point
TEXNICA TPCS 1.0 — FOUR-POINT
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Inspection ID | Inspection Date | Receiving Number | Fabric PO Number | FGPO | Lot Number | Roll Number | Width (in) | Inspected Length (yd) | 1-Point | 2-Point | 3-Point | 4-Point | Total Points | Points / 100 sq yd | Max Allowed | Accepted Qty | Rejected Qty | Hold Qty | Result | Inspector | Report Link | Last Updated | Comments

## Internal Test
TEXNICA TPCS 1.0 — INTERNAL TEST
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Internal Test ID | Test Date | Fabric PO Number | FGPO | Lot Number | Color | Actual Width | Specimen Area cm² | Weight Before g | GSM Before | Weight After g | GSM After | Target GSM | GSM Variance % | Length Before | Length After | Length Shrinkage % | Width Before | Width After | Width Shrinkage % | Torque % | Bowing % | Skewing % | Shade Result | Wash Appearance | Hand Feel | Test Result | Tested By | Approved By | Report Link | Last Updated | Comments

## Shade Match
TEXNICA TPCS 1.0 — SHADE MATCH
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Match ID | Review Date | FGPO | Style | Color | Body Fabric Lot | Rib Lot | Shoulder Tape Lot | Body Shade Group | Rib Shade Group | Tape Shade Group | Body vs Rib | Body vs Tape | Light Source | Before Wash Result | After Wash Result | Overall Result | Approved By | Report Link | Last Updated | Comments

## Fabric Approval
TEXNICA TPCS 1.0 — FABRIC APPROVAL
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Approval ID | Approval Date | Fabric PO Number | FGPO | Lot Number | Receiving Completed | Four-Point Result | Internal Test Result | Shade Match Result | Shrinkage Status | Torque Status | GSM Status | Width Status | Authorized Quantity | Exception Reason | Approved By | Final Status | Released for Cutting Date | Data Owner | Last Updated | Comments

## Fabric Inventory
TEXNICA TPCS 1.0 — FABRIC INVENTORY
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Inventory ID | Fabric PO Number | FGPO | Fabric Component | Lot Number | UOM | Received Quantity | Approved Quantity | Rejected Quantity | Hold Quantity | Reserved Quantity | Issued Quantity | Returned Quantity | Available Quantity | Shortage Quantity | Warehouse Location | Inventory Status | Data Owner | Last Updated | Remarks

## Fabric Reservation
TEXNICA TPCS 1.0 — FABRIC RESERVATION
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Reservation ID | Reservation Date | Fabric PO Number | FGPO | Fabric Component | Lot Number | Reserved Quantity | UOM | Released Quantity | Remaining Reservation | Status | Reserved By | Approved By | Last Updated | Comments

## Issue to Cutting
TEXNICA TPCS 1.0 — ISSUE TO CUTTING
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Issue Number | Issue Date | FGPO | Fabric PO Number | Style | Color | Fabric Component | Lot Number | Roll Number | Issued Quantity | UOM | Issued Weight | Marker Number | Cutting Table | Issued By | Received By Cutting | Returned Quantity | End Bits / Waste | Net Consumption | Approval Status | Data Owner | Last Updated | Remarks

## Trims Control
TEXNICA TPCS 1.0 — TRIMS CONTROL
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Trim Record ID | FGPO | Style | Color | Trim Type | Description | Supplier | UOM | Consumption / Garment | Required Qty | Ordered Qty | Received Qty | Approved Qty | Rejected Qty | Reserved Qty | Issued Qty | Available Qty | Shortage Qty | ETA | Development Status | Approval Status | Availability Status | Data Owner | Last Updated | Comments

## PP Sample
TEXNICA TPCS 1.0 — PP SAMPLE
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Sample ID | FGPO | Style | Color | Size | Sample Version | Fabric Lot | Trim Version | Preparation Date | Submission Date | Measurement Result | Construction Result | Fit Result | Fabric Result | Trim Result | Label Result | Internal Review | Customer Review | Customer Comments | Approval Date | Approved By | Status | Document Link | Photo Link | Last Updated

## Production Readiness
TEXNICA TPCS 1.0 — PRODUCTION READINESS
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
PRR ID | Review Date | FGPO | Style | Color | PO Confirmed | Tech Pack Current | Fabric Approved | Trims Approved | Trims Available | PP Sample Approved | Pattern Approved | Marker Approved | Fabric Width Confirmed | Shrinkage Approved | Torque Approved | Quality Standard Ready | Line Planned | Overall Result | Open Conditions | Responsible Owner | Due Date | Approved By | Last Updated

## Cutting Release
TEXNICA TPCS 1.0 — CUTTING RELEASE
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Release Number | Release Date | FGPO | Style | Color | Fabric Lot | Approved Cut Qty | Approved Width | Marker Number | Approved Yield | PRR Result | Released By | Reviewed By | Exception | Conditions | Release Status | Last Updated | Comments

## Cutting Control
TEXNICA TPCS 1.0 — CUTTING CONTROL
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Cut Record ID | Date | FGPO | Style | Color | Size | Fabric Lot | Marker Number | Planned Cut | Actual Cut | Good Cut | Damaged Qty | Replacement Cut | Sent to Sewing | Cutting Variance | Pending Cut | Overcut Qty | Cut-to-Sew Difference | Release Status | Responsible Person | Last Updated | Comments

## Cutting Panel QC
TEXNICA TPCS 1.0 — CUTTING PANEL QC
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Inspection ID | Date | FGPO | Style | Color | Size | Fabric Lot | Cut Lot / Lay | Bundle No. | Sample Qty | Panel Defects | Notches Defects | Drill Mark Defects | Shade Defects | Measurement Defects | Total Defects | Defect Rate % | Max Allowed | Result | Inspector | Corrective Action | Last Updated | Comments

## TOP Sample
TEXNICA TPCS 1.0 — TOP SAMPLE
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
TOP ID | FGPO | Style | Color | Size | Production Line | Fabric Lot | Cut Lot / Bundle | Trim Version | Thread Lot | TOP Qty | Production Date | Measurement Result | Construction Result | Workmanship Result | Label Result | Packing Result | Internal Review | Customer Review | Corrective Action | Approval Date | Approved By | Status | Document Link | Photo Link | Last Updated

## Sewing Production
TEXNICA TPCS 1.0 — SEWING PRODUCTION
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Record ID | Date | Shift | Line | FGPO | Style | Color | Size | Sewing Input | Daily Target | Daily Output | Cumulative Output | WIP | Rework | Reject | Downtime Minutes | Target Achievement % | Sewing Variance | Pending Sewing | Overproduction | TOP Status | Supervisor | Last Updated | Problems / Remarks

## Inline Quality
TEXNICA TPCS 1.0 — INLINE QUALITY
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Inspection ID | Date | Time | Line | FGPO | Style | Color | Operation | Operator | Checked Qty | Critical Defects | Major Defects | Minor Defects | Total Defects | DHU % | Defective Pieces | Defective Rate % | Max Allowed | Result | Inspector | Immediate Correction | Root Cause / Follow-up | Last Updated

## Endline Inspection
TEXNICA TPCS 1.0 — ENDLINE INSPECTION
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Inspection ID | Inspection Date | FGPO | Style | Color | Lot / Shipment | Lot Size | Inspection Level | AQL Major | AQL Minor | Sample Size | Critical Defects | Major Defects | Minor Defects | Critical Ac | Major Ac | Minor Ac | Critical Re | Major Re | Minor Re | Result | Inspector | Disposition | Report Link | Last Updated | Comments

## Pre-Final Inspection
TEXNICA TPCS 1.0 — PRE-FINAL INSPECTION
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Inspection ID | Inspection Date | FGPO | Style | Color | Lot / Shipment | Lot Size | Inspection Level | AQL Major | AQL Minor | Sample Size | Critical Defects | Major Defects | Minor Defects | Critical Ac | Major Ac | Minor Ac | Critical Re | Major Re | Minor Re | Result | Inspector | Disposition | Report Link | Last Updated | Comments

## Final Inspection
TEXNICA TPCS 1.0 — FINAL INSPECTION
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Inspection ID | Inspection Date | FGPO | Style | Color | Lot / Shipment | Lot Size | Inspection Level | AQL Major | AQL Minor | Sample Size | Critical Defects | Major Defects | Minor Defects | Critical Ac | Major Ac | Minor Ac | Critical Re | Major Re | Minor Re | Result | Inspector | Disposition | Report Link | Last Updated | Comments

## Packing Control
TEXNICA TPCS 1.0 — PACKING CONTROL
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Packing Record ID | Date | FGPO | Style | Color | Size | QC Passed Qty | Received by Packing | Folded Qty | Polybagged Qty | Packed Qty | Full Cartons | Partial Cartons | Pcs per Carton | Ready to Ship Qty | Packing Variance | Pending Packing | Overpacked Qty | Responsible Person | Last Updated | Remarks

## Finished Goods
TEXNICA TPCS 1.0 — FINISHED GOODS
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
FG Record ID | Receipt Date | FGPO | Style | Color | Size | Packed Qty | Warehouse Received | Reserved for Shipment | Ready to Ship | Loaded Qty | Shipped Qty | Warehouse Balance | Warehouse Location | Status | Data Owner | Last Updated | Remarks

## Shipment Control
TEXNICA TPCS 1.0 — SHIPMENT CONTROL
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Shipment Number | Customer | FGPO | Style | Color | Size | Planned Qty | Actual Loaded Qty | In Transit Qty | Customer Received Qty | Total Shipped Qty | Shipment Variance | Pending to Ship | Over-shipment Qty | Container Type | Container Number | Booking Number | Planned Loading Date | Actual Loading Date | ETD | ETA | Destination | Shipment Status | Packing List | Invoice Number | Load Plan | Data Owner | Last Updated | Remarks

## Open Issues
TEXNICA TPCS 1.0 — OPEN ISSUES
Yellow cells = input ¦ Gray cells = automatic formulas ¦ Use one official record per transaction
Issue ID | Open Date | Priority | FGPO | Style | Color | Area | Issue Type | Description | Quantity Affected | Ship Date Impact | Immediate Action | Corrective Action | Owner | Due Date | Status | Evidence Link | Closing Date | Verified By | Last Updated

## Lists
General Status | Test Result | Approval | UOM | Fabric Component | Shipment Status | Receiving Status | Risk | Threshold | Value
Not Started | Pending | Pending | Yards | Body Fabric | Planned | Pending | Green | 4-Point Max / 100 sq yd | 40
Pending | Testing | Approved | Meters | Rib | Booking Confirmed | Partially Received | Yellow | Length Shrinkage Limit | 5%
In Progress | Passed | Conditionally Approved | Kilograms | Shoulder Tape | Exported | Fully Received | Red | Width Shrinkage Limit | 5%
Partially Completed | Conditionally Passed | Rejected | Pounds | Neck Tape | In Transit | Quantity Difference | Gray | Torque Limit | 5%
Completed | Failed | On Hold | Rolls | Pocketing | Customs Processing | On Hold |  | GSM Variance Limit | 5%
Approved | Retest Required | Released for Cutting | Pieces | Other | Arrived | Closed |  | Receiving Tolerance | 0%
Conditionally Approved | On Hold |  |  |  | Delivered
Rejected |  |  |  |  | Closed
On Hold
Closed
Cancelled
FGPO Pending